## Blad1
Importance - 1 least, 5 most | use cases | Story Points
5 | Move player | 4
5 | Start game | 4
5 | Fetch twitter feed | 36
5 | Enter new room | 36
3 | Start fight | 16
1 | Item description | 6
2 | Combine items | 36
3 | Use item | 12
3 | Pick up item | 12
3 | Drop item | 18
1 | Give item | 72
1 | Use item on character | 72
4 | Open/Close inventory | 36
1 | Player to character interaction | 72
5 | Start menu | 12
5 | Start new single player game | 12
1 | Start multiplayer game | 72
5 | Create character | 6
1 | Player chat | 36
Total |  | 570
Prio 5 |  | 110
Prio 4 |  | 36
Prio 3 |  | 58
Prio 2 |  | 36
Prio 1 |  | 330
Total points 240 per iteration
Iteration 1
Prio | Use cases | Max | Min | Average
5 | Start menu | 12 | 6 | 8
5 | Start single player | 12 | 6 | 8
5 | Start game | 4 | 2 | 4
4 | Move player | 4 | 2 | 4
5 | Fetch twitter feed | 36 | 12 | 24
5 | Enter new room | 36 | 12 | 24
5 | Create character | 6 | 2 | 4
Total points |  | 110 | 42 | 76
Iteration 2
Prio | Use cases | Max | Min | Average
4 | Open/Close inventory | 36 | 12 | 24
3 | Pick up item | 12 | 2 | 6
3 | Drop item | 18 | 4 | 12
3 | Use item | 12 | 4 | 8
3 | Start fight | 16 | 4 | 10
2 | Combine items | 36 | 12 | 24
Total points |  | 130 | 38 | 84
Iteration 3
Prio | Use cases | Max | Min | Average
1 | Player interaction | 72 | 12 | 36
1 | Use item on character | 72 | 12 | 36
1 | Give item | 72 | 12 | 36
1 | Item description | 6 | 2 | 4
1 | Start multiplayer | 72 | 12 | 36
Total points |  | 294 | 50 | 148