## Blad1
Task | Dealine | Start Date | End Date(08:00) | Responsible | Estimate week hr | Actual time spent hr | Progress
Release Sprint 1 | 2017-06-04 | 29/3 | 2017-07-04 |  | 16 | 20h | Started
Release Sprint 2 | 2017-11-04 | 29/3 | 2017-12-04 |  | 40 | 2h | Started
Release Sprint 3 | 2017-02-05 | 30/3 | 2017-03-05 |  | 16 | -
Release Sprint 4 | 16/5 | 2017-04-05 | 17/5 |  | 32 | -
Release sprint 2 | To do |  | Estimate hr | Estimate start | Estimate Deadline | Responsible | Progress | Actual time spent hr
| User Stories |  | 12 | 2017-04-04 | 2017-04-04 | Teemu
Requirement document
Renskriva User Stories
| Use Case Overview |  | 16 | 2017-05-04 | 2017-07-04 | Noah
Use case diagrams
| Implementation plan |  | 4 | 2017-07-04 | 2017-10-04 | Jakob
Prioritera use case diagrams
Assign story points
Iterationplan
| Detailed use cases for first iteration |  | 8 | 2017-07-04 | 2017-10-04 | Jonatan
tabellvarianten
Release Sprint 3