## Blad1
Total points 240 per iteration
importance | use cases | Max Points | Min Points | Average Points | Comments
5 | Move Player* | 4 | 2 | 4
5 | Start Game* | 4 | 2 | 4
5 | Fetch Twitter Feed | 36 | 12 | 24
5 | Enter New Room | 36 | 12 | 24
3 | Start Fight | 16 | 4 | 10
1 | Item Description | 6 | 2 | 4
2 | Combine Items | 36 | 12 | 24
3 | Use Item | 12 | 4 | 8
3 | Pick up Item | 12 | 2 | 6
3 | Drop Item | 18 | 4 | 12
1 | Give Item | 72 | 1 | 36 | No Estimate
1 | Use Item On Character | 72 | 1 | 36 | No Estimate
4 | Open/Close Inventory | 36 | 12 | 24
1 | Player interaction | 72 | 12 | 36 | No Estimate
5 | Start Menu* | 12 | 6 | 8
5 | Start Singleplayer* | 12 | 6 | 8
1 | Start Multiplayer | 72 | 1 | 36 | No Estimate
5 | Create character | 6 | 2 | 4
Total |  | 534 | 97 | 308
Prio 5 |  | 110 | 42 | 76
Prio 4 |  | 36 | 12 | 24
Prio 3 |  | 58 | 14 | 36
Prio 2 |  | 36 | 12 | 24
Prio 1 |  | 294 | 6 | 148
Iteration 1
Prio | Use cases | Max | Min | Average
5 | Start Menu | 12 | 6 | 8
5 | Start Singleplayer | 12 | 6 | 8
5 | Start Game | 4 | 2 | 4
4 | Move Player | 4 | 2 | 4
5 | Gather Twitter Feed | 36 | 12 | 24
5 | Enter New Room | 36 | 12 | 24
5 | Create character | 6 | 2 | 4
Total points |  | 110 | 42 | 76
iteration 2
Prio | Use cases | Max | Min | Average
4 | Open/Close inventory | 36 | 12 | 24
3 | Pick up item | 12 | 2 | 6
3 | Drop item | 18 | 4 | 12
3 | Use item | 12 | 4 | 8
3 | Start fight | 16 | 4 | 10
2 | Combine items | 36 | 12 | 24
Total points |  | 120 | 40 | 84
Iteration 3
Prio | Use cases | Max | Min | Average
1 | Player interaction | 72 | 12 | 36
1 | Use item on character | 72 | 1 | 36
1 | Give item | 72 | 1 | 36
1 | Item description | 6 | 2 | 4
1 | Start multiplayer | 72 | 1 | 36
Total points |  | 294 | 17 | 148